Predictive Risk Identification for Diabetes and Heart Disease

Project Status Report, Gap Analysis & Comprehensive Roadmap

Project Metadata & Audit Scope

| Field | Detail |
| --- | --- |
| Role | Project Auditor & Technical Writer |
| Evaluation Scope | All Code, Data, Notebooks, Models, Outputs, and Reports |
| Current Status | 50% Complete (Stages 1 & 2 Complete; Stage 3 Pending) |
| Target Models | Logistic Regression, Decision Tree, Random Forest + SHAP |
| Evaluation Metrics | F1-Score, ROC-AUC, Recall / Sensitivity (Separate Per Disease) |
| Audit Date | October 2026 |

Executive Summary: Current Completion Level = 50% One-Line Justification: The project has completed thorough, high-quality data cleaning, dataset integration, exploratory data analysis, frequent pattern mining, unsupervised clustering, dimensionality reduction, and outlier diagnostics (Stages 1 & 2), but has NOT yet implemented supervised predictive modeling, model comparison, evaluation metrics (F1/ROC-AUC/Recall), SHAP explainability, or the interactive new-patient inference interface (Stage 3).

# 1. Work Completed So Far

The project repository reflects two successfully delivered milestones: Stage 1 (Mid-Term Report: Preprocessing, Missing Data Science, Integration, and Frequent Pattern Mining) and Stage 2 (Clustering, Dimensionality Reduction, and Anomaly Diagnostics). Below is an evidence-based audit of each completed step.

## 1.1 Data Loading & Workspace Inventory

A complete inventory was conducted across all 8 raw CSV files in the workspace (totaling 1,590,066 records). Four benchmark datasets totaling 699,877 records were selected for primary clinical and population analysis:
• UCI Pima Indians Diabetes (data/raw/diabetes.csv): 768 patient records across 9 clinical lab features (34.90% diabetes).
• UCI Cleveland Heart Disease (data/raw/heart_cleveland_upload.csv): 297 patient records across 14 cardiac features (46.13% disease).
• CDC BRFSS 2015 Health Indicators: 253,680 survey records across 22 questions with dual disease outcomes (13.93% diabetes, 9.42% heart disease).
• CDC Heart 2022 (with NaNs): 445,132 records used as a benchmark for real-world survey missingness mechanisms.

Table 1: Complete Dataset Inventory in Workspace

| Filename | Description | Rows | Columns | Size Mb | Selected | Reason |
| --- | --- | --- | --- | --- | --- | --- |
| diabetes.csv | UCI Pima Indians Diabetes | 768 | 9 | 0.02 | True | Primary clinical or survey benchmark |
| heart_cleveland_upload.csv | UCI Cleveland Heart Disease | 297 | 14 | 0.01 | True | Primary clinical or survey benchmark |
| diabetes_binary_health_indicators_BRFSS2015.csv | CDC BRFSS 2015 (Binary Outcome) | 253680 | 22 | 21.68 | True | Primary clinical or survey benchmark |
| diabetes_binary_5050split_health_indicators_BRFSS2015.csv | CDC BRFSS 2015 (50/50 Balanced Split) | 70692 | 22 | 6.05 | False | Derivative or redundant split |
| diabetes_012_health_indicators_BRFSS2015.csv | CDC BRFSS 2015 (3-Class Outcome) | 253680 | 22 | 21.68 | False | Derivative or redundant split |
| heart_2020_cleaned.csv | CDC BRFSS 2020 (Pre-cleaned) | 319795 | 18 | 24.02 | False | Derivative or redundant split |
| heart_2022_no_nans.csv | CDC BRFSS 2022 (No NaNs) | 246022 | 40 | 78.19 | False | Derivative or redundant split |
| heart_2022_with_nans.csv | CDC BRFSS 2022 (Raw with NaNs) | 445132 | 40 | 133.39 | True | Primary clinical or survey benchmark |

## 1.2 Data Preprocessing & Missing Data Science

Data cleaning and quality audits were executed via src/02_clean.py, src/02b_clean_brfss.py, and src/project_pipeline.py:
• Pima Hidden Zeros Audit: Uncovered 652 hidden zeros across 376 individual patient rows (48.96% of cohort). These zeros represented test omissions in continuous biometrics where a true zero is biologically impossible: Insulin (374 rows, 48.70%), Skinfold Thickness (227 rows, 29.56%), Diastolic BP (35 rows, 4.56%), BMI (11 rows, 1.43%), and Glucose (5 rows, 0.65%). All impossible zeros were replaced with NaN in data/clean/pima_clean.csv. Pregnancies zeros (111 rows, 14.45%) were preserved as valid nulliparous counts.
• Survey Missingness & Duplicates: In CDC Heart 2022, listwise deletion was shown to drop 44.73% of records (199,110 rows), whereas preserving observed targets dropped only 0.69%. In CDC BRFSS 2015, 24,206 duplicate rows (9.54%) were identified and intentionally retained, as discrete survey profiles from 253,680 people naturally produce identical responses.
• Vertical Dataset Integration: Vertically merged Pima (768), Cleveland (297), and a stratified sample of BRFSS (25,000) into data/clean/integrated_dataset.csv (26,065 rows, 13 harmonized columns). Documented structural missingness by design: lab values are absent in survey data (Cholesterol 98.86%, Glucose 97.07%, BP 96.05%, Insulin 98.49% missing).
• Normalization & Transformations: Tested Min-Max, Z-score, and log1p transformations. Insulin skewness improved from +2.17 to -0.09. Age log-transformation was proven contraindicated, worsening skewness from -0.36 to -1.01.

Table 2: Pima Indians Diabetes Hidden Zero Audit

| Variable | Zero Placeholder Count | Percent Missing | Clinical Mechanism |
| --- | --- | --- | --- |
| Glucose | 5 | 0.65 | Fasting plasma glucose draw skipped during field evaluation. |
| BloodPressure | 35 | 4.56 | Sphygmomanometer test omitted or inaudible diastolic Korotkoff sounds. |
| SkinThickness | 227 | 29.56 | Triceps skinfold caliper measurement omitted due to patient discomfort or protocol bypass. |
| Insulin | 374 | 48.70 | 2-hour serum insulin after 75g oral glucose tolerance challenge omitted (invasive and costly). |
| BMI | 11 | 1.43 | Weight or standing height unrecorded during clinical intake. |
| Pregnancies | 0 | 0.00 | Valid biological zero: 111 women (14.45%) are nulliparous. |

## 1.3 Frequent Pattern Mining & Association Rules

Conducted frequent pattern mining on 25,000 transactions (15 binary items) using Apriori and FP-Growth:
• Algorithm Benchmark: Verified exact itemset equivalence at min_support = 0.20 (72 identical itemsets). FP-Growth executed faster (0.0031s vs 0.0041s).
• Support Sensitivity: Evaluated support thresholds across [0.40, 0.30, 0.20, 0.10, 0.05]. At 0.05, 611 itemsets and 5,836 association rules emerged.
• Top Population Rules: {HighChol, BMI>=30, Age>=50} -> Diabetes (Confidence: 35.66%, Lift: 2.58 vs. 13.93% baseline). {HighChol, HighBP, Age>=50} -> HeartDisease (Confidence: 23.00%, Lift: 2.43 vs. 9.46% baseline).
• Clinical Benchmark Rules: In Pima, {Age>=35, Glucose>125, BMI>=30} -> Diabetes yielded 77.06% confidence (Lift: 2.21). In Cleveland, {Male, HighChol>=240, ExAngina} -> HeartDisease yielded 90.24% confidence (Lift: 1.96).

## 1.4 Unsupervised Clustering, Dimensionality Reduction & Outlier Diagnostics

Executed Stage 2 unsupervised machine learning via src/stage2_pipeline.py:
• Clustering Models: Benchmarked K-Means (k=3), Hierarchical Agglomerative (Ward linkage, k=3), and DBSCAN (eps=2.4, minPts=5). K-Means (k=3) achieved Silhouette = 0.1534, Davies-Bouldin = 2.1061, and Calinski-Harabasz = 860.45. Discovered 3 clinical phenotypes: Cluster 0 (Low Risk, 46.8%, 3.2% diabetes, 1.8% heart disease), Cluster 1 (Moderate Overweight, 39.1%, 21.6% diabetes, 14.4% heart disease), and Cluster 2 (Multi-Morbidity Crisis, 14.1%, 27.0% diabetes, 23.0% heart disease).
• Dimensionality Reduction: PCA decomposed 11 features into PC1 (24.78% variance; physical deterioration) and PC2 (13.91% variance; vascular aging). Top 6 PCs retain 73.98% variance. Re-clustering on 6 PCs improved Silhouette by +33.4% (to 0.2046) and reduced Davies-Bouldin by -19.0% (to 1.7054).
• Outlier Detection: Isolation Forest identified 175 outliers (3.5% contamination). Outliers represent severe multi-morbidity (avg BMI 33.4, max 82.0, 24.9 days/month impaired, 29.7% diabetes, 25.1% heart disease). Pruning outliers restored cluster centroids toward realistic population medians.

Table 3: Health and Biometric Profiles across K-Means Clusters

| Cluster Id | Clinical Designation | Sample Size N | Percent Cohort | Avg Age Years | Avg Bmi | Hypertension Rate Pct | High Cholesterol Pct | Smoker Rate Pct | Phys Activity Pct | Avg Poor Phys Days | Avg Poor Ment Days | Diabetes Prevalence Pct | Heart Disease Pct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cluster 0 | Cluster 0: Low-Risk / Active Young Cohort | 2339 | 46.80 | 49.60 | 26.90 | 8.00 | 18.10 | 32.00 | 87.70 | 1.10 | 1.70 | 3.20 | 1.80 |
| Cluster 1 | Cluster 1: Moderate-Risk / Overweight Metabolic | 1956 | 39.10 | 65.70 | 29.50 | 78.30 | 67.60 | 54.70 | 68.80 | 1.50 | 1.10 | 21.60 | 14.40 |
| Cluster 2 | Cluster 2: High-Risk / Elderly Multi-Morbidity | 705 | 14.10 | 59.10 | 31.00 | 62.60 | 53.00 | 59.90 | 50.50 | 21.40 | 13.00 | 27.00 | 23.00 |

Figure 1: 2D Manifold Visualizations — PCA vs. t-SNE Projections Colored by Risk Clusters and Diagnoses

Key Finding: PCA and t-SNE cleanly segregate Low-Risk healthy respondents from High-Risk multi-morbidity patients.

## 1.5 Supervised Machine Learning & Explainability (Current Status)

Plain-Truth Audit: Supervised model training, evaluation, and explainability work have NOT YET BEEN IMPLEMENTED. Specifically: no classification models (Logistic Regression, Decision Tree, Random Forest) have been trained or evaluated; no F1, ROC-AUC, or Recall metrics have been generated; and no SHAP global summary or patient-level waterfall plots exist in the repository.

# 2. Current State vs. The End Product (Gap Analysis)

The table below details every explicit project requirement against actual files and outputs in the workspace:

Table 4: Comprehensive Gap Analysis against Required End Product

| Requirement | Status | Evidence | What Is Missing |
| --- | --- | --- | --- |
| Clean, merged, model-ready dataset | Partial | data/clean/integrated_dataset.csv, pima_clean.csv, cleveland_clean.csv, brfss_clean.csv | Merged dataset has 96-98% structural missingness for lab values. Dedicated feature matrices (X, y) split into train/test folds have not been built. |
| Risk prediction model for diabetes | Not started | None | No supervised model (Logistic Regression, Decision Tree, Random Forest) trained for diabetes prediction. |
| Risk prediction model for heart disease | Not started | None | No supervised model trained for heart disease prediction. |
| Model comparison & best-model selection | Not started | None | No cross-validation benchmark or selection criteria comparing algorithms. |
| Evaluation with F1, ROC-AUC, Recall | Not started | None | No evaluation metrics, ROC curves, PR curves, or confusion matrices exist for supervised predictions. |
| Global feature importance | Partial | stage2_pca_loadings.csv, top_diabetes_rules_by_lift.csv | Only unsupervised PCA loadings and rule lift exist. Supervised Gini importance, logistic weights, and global SHAP values are missing. |
| Patient-level explanation of risk variables | Not started | None | No SHAP TreeExplainer/LinearExplainer or local waterfall/force plots explaining individual patients. |
| Input a new patient & get risk + top variables | Not started | None | No interactive script, function, CLI, or UI accepting user inputs and outputting risk predictions + explanations. |
| Final report and presentation | Partial | stage2_report.pdf (20 pages), mid_report_v2.pdf (18 pages) | Mid-term and Stage 2 reports are complete, but final Stage 3 report and presentation slides are not yet authored. |

# 3. Key Findings So Far

Quantitative findings from data preprocessing, pattern mining, and unsupervised clustering:
• Baseline Population Disease Burden: In CDC BRFSS (N=253,680), diabetes prevalence is 13.93% (35,346 positive cases) and heart disease prevalence is 9.42% (23,893 positive cases), reflecting class imbalance ratios of ~6.2:1 and ~9.6:1 respectively.
• Age & Vascular Aging: Age has the single highest positive loading on PCA Component 2 (+0.5740). Population association rules indicate that Age>=50 serves as a requisite gatekeeper for cardiometabolic escalation.
• Hypertension (HighBP): HighBP loads strongly on PC2 (+0.4215) and PC1 (+0.3034). Prevalent in 78.3% of Moderate-Risk cluster patients and 62.6% of High-Risk cluster patients, compared to only 8.0% of Low-Risk individuals.
• High Cholesterol (HighChol): Loads heavily on PC2 (+0.4574). Paired with HighBP and Age>=50, it elevates population heart attack probability by 2.43x baseline (Confidence: 23.00%). In Cleveland angiography, HighChol>=240 paired with exercise angina predicted heart disease with 90.24% confidence.
• General & Physical Health Days: GenHlth (+0.4692) and PhysHlth (+0.3838) dominate PC1. Normal inliers report 3.4 days/month of poor physical health vs. 24.9 days/month for high-acuity outliers.
• Fasting Glucose in Clinical Cohorts: Fasting glucose >125 mg/dL in Pima predicts diabetes with 77.06% confidence when combined with BMI>=30 and Age>=35.

Figure 2: Outlier Diagnostics — Manifold Embeddings and Biometric Distribution Contrasts

Key Finding: Isolation Forest outliers exhibit dramatic elevations in BMI (up to 82.0 kg/m²) and physical health impairment (24.9 days/month).

# 4. Problems, Risks, and Limitations

Critical analytical and technical constraints identified during the audit:
1. Structural Missingness in Merged Cohort: In integrated_dataset.csv, continuous lab tests (glucose, insulin, continuous BP, cholesterol) are absent in over 96% to 98% of rows because the CDC survey records only binary questions. Training a single model directly on the merged dataset would introduce severe bias. Separate models must be trained per disease cohort or trained on survey-common features.
2. Severe Class Imbalance: Both disease targets in the survey cohort are heavily skewed (~90% negative vs ~10% positive). Standard accuracy is misleading (a naive dummy classifier achieves >90% accuracy). Evaluation must strictly prioritize Recall, F1, and ROC-AUC.
3. Small Clinical Cohort Sizes: UCI Cleveland (N=297) and UCI Pima (N=768) are small clinical datasets compared to CDC BRFSS (N=253,680), making clinical models vulnerable to overfitting if regularized hyperparameters are not enforced.
4. Target Proxy Circularity Risk: high_glucose in BRFSS was mapped directly from Diabetes_binary (r=0.97). While removed from the EDA heatmap, it must strictly be excluded as an input feature in supervised modeling to avoid trivial target leakage.
5. Survey Recall Bias: CDC BRFSS relies on self-reported phone survey responses, subject to recall bias and lack of longitudinal verification.

# 5. Prioritized Roadmap to Complete the End Product

To advance the project from 50% to 100% completion, the following 5 sequential phases must be executed:

Table 5: Prioritized Step-by-Step Implementation Roadmap

| Phase | Key Tasks | Files To Create Or Modify | Effort Estimate |
| --- | --- | --- | --- |
| Phase 1: Feature Matrices & Leakage-Free Splitting | Build separate model-ready datasets (Population Survey vs. Clinical Lab); implement stratified 80/20 train/test splits; build scikit-learn Pipelines with median/robust scaling. | src/03_model_preprocessing.py, data/clean/diabetes_model_ready.csv, data/clean/heart_model_ready.csv | 4 - 6 Hours |
| Phase 2: Supervised Model Training | Train separate models for Diabetes and Heart Disease across Logistic Regression, Decision Tree, and Random Forest; tune hyperparameters via GridSearchCV; handle class imbalance via class_weight='balanced' and SMOTE. | src/04_train_models.py, models/diabetes_*.joblib, models/heart_*.joblib | 6 - 8 Hours |
| Phase 3: Model Evaluation & Best Selection | Evaluate held-out test sets on F1-Score, ROC-AUC, Recall (Sensitivity); generate comparative benchmark tables, ROC curves, PR curves, and confusion matrices; select champion model. | src/05_evaluate_models.py, outputs/tables/model_comparison_metrics.csv, outputs/figures/stage3_roc_pr_curves.png | 5 - 6 Hours |
| Phase 4: Global & Local SHAP Explainability | Compute SHAP values using TreeExplainer and LinearExplainer; generate global summary beeswarm plots; implement patient-level waterfall plots explaining exact variables pushing risk. | src/06_explainability_shap.py, outputs/figures/shap_summary_plots.png, outputs/figures/shap_patient_waterfall.png | 6 - 8 Hours |
| Phase 5: Interactive Patient Inference Tool & Final Report | Develop CLI/interactive script where user enters patient biometrics and gets predicted risk + top 3 pushing factors; compile final Stage 3 report and presentation slides. | src/predict_patient.py, src/build_final_report.py, stage3_final_report.docx/.pdf, final_presentation.pptx | 6 - 8 Hours |

Total Estimated Remaining Effort Total Estimated Implementation Time: 27 – 36 Working Hours (approximately 4 to 5 working days). Execution Path: Preprocessing -> Model Training -> Multi-Metric Evaluation -> SHAP Explainability -> Interactive Triage Interface -> Final Report.

Audit Sign-off:
Verified against repository filesystem, data pipelines, output tables, and compiled reports.
Report Output: PROJECT_STATUS_REPORT.pdf | Date: October 2026